## Problems
reference (e.g. CR) | MTOSI R2.0 file | location in the file | problem identified | solution proposed | solution implemented when | new file version
| FMW/SD/SD1-18 | top of p 10 | typo: bullet: ITU-T members + "(see… G.805)" | fix the typo and create a new version of the file | 2009-12-28 | 3.4
| TMF518_NRF | section 3.1.13 | error reference; the file under "Product/trunk" is correct; it seems that the file in "main" is not the correct one. | No need to change the file under "Product/trunk"; instead reuse this file in main and when packaging release 2.1
| TMF518_NRF |  | navigation does not work in PDF (works in Word) | need to re-generate the PDF (using the correct Word file)
| FMW/SD/SD0-1_mTOPDictionary.pdf | section 1.2 | ??? TBD: | fix the typo and create a new version of the file | 2009-12-28 | 1.2
| FMW/SD/SD0-4_mTOPGuidelines_IA.pdf |  | "to be defined", highlighted in blue at different places | The Word file in "main" is correct (the pdf was generated from a previous version); need to regenerate the pdf in "main"and repackage.
| FMW/SD/SD0-5_mTOPGuidelines_WebServices.pdf |  | section 1.1: reference to wiki on Gforge | reformulate the satement
| FMW/SD/SD0-5_mTOPGuidelines_WebServices.pdf |  | section 7.2: some references are not navigable | fix the hyperlinks to relative reference | 2009-12-28 | 1.1
| NetworkResourceFulfillment/SD/SD2-20_EquipmentModel.pdf |  | hyperlinks are not navigable | The Word file in "main" is correct; need to regenerate the pdf and check, then repackage.
| NetworkResourceFulfillment/SD/SD1-7_DSLOverview.pdf |  | references should not have the "pdf" suffix | Remove the ".pdf" extension in the textToDisplay of the hyperlinks | 2009-12-28 | 3.2
| ServiceBasic\BA |  | file "SD2-19_VoIPServiceDefinition.pdf" should not be here | "Product\trunk\ServiceBasic\BA" is correct; remove this file from "main\DDPs\ServiceBasic\BA"